## Company Information
Company Name | Org A Member 2
Reporting Period | May 2026
Submission Date | 2026-05-10
Prepared By | Org A Member 2

## Quality Data
Org A Member 2
Reporting Period: May 2026
This template collects Quality KPIs including technical submittal performance, inspection acceptance rates, NCR management, and audit completion. All figures are cumulative up to the data date.
Work Package | Total Technical Submittals | Code A (Accepted) | Code B (Accepted w/ Comments) | Code C (Rejected) | Planned Quality Audits | Conducted Quality Audits | Leadership Visits | Received MIRs | Accepted MIRs | Received WIRs | Accepted WIRs | Raised NCRs | Closed NCRs
Work Package | Total Technical Submittals | Code A (Accepted) | Code B (Accepted w/ Comments) | Code C (Rejected) | Planned Quality Audits | Conducted Quality Audits | Leadership Visits | Received MIRs | Accepted MIRs | Received WIRs | Accepted WIRs | Raised NCRs | Closed NCRs
Design & Engineering | 145 | 128 | 15 | 2 | 18 | 16 | 3 | 420 | 408 | 315 | 302 | 4 | 4
Procurement & Logistics | 88 | 71 | 14 | 3 | 12 | 11 | 2 | 280 | 271 | 198 | 190 | 3 | 2
Construction – Phase 1 | 210 | 185 | 21 | 4 | 26 | 24 | 5 | 680 | 655 | 510 | 488 | 9 | 7
TOTAL | Submittal Approval Rate |  |  |  | Audit Completion Rate |  |  | MIR Acceptance Rate |  | WIR Acceptance Rate |  | NCR Closure Rate
KPI RATES