## Company Information
Company Name | Org B Member 2
Reporting Period | May 2026
Submission Date | 2026-05-10
Prepared By | Org B Member 2

## Quality Data
Org B Member 2
Reporting Period: May 2026
This template collects Quality KPIs including technical submittal performance, inspection acceptance rates, NCR management, and audit completion. All figures are cumulative up to the data date.
Work Package | Total Technical Submittals | Code A (Accepted) | Code B (Accepted w/ Comments) | Code C (Rejected) | Planned Quality Audits | Conducted Quality Audits | Leadership Visits | Received MIRs | Accepted MIRs | Received WIRs | Accepted WIRs | Raised NCRs | Closed NCRs
Work Package | Total Technical Submittals | Code A (Accepted) | Code B (Accepted w/ Comments) | Code C (Rejected) | Planned Quality Audits | Conducted Quality Audits | Leadership Visits | Received MIRs | Accepted MIRs | Received WIRs | Accepted WIRs | Raised NCRs | Closed NCRs
Civil – Substructure | 198 | 172 | 22 | 4 | 24 | 21 | 4 | 580 | 558 | 440 | 420 | 7 | 5
Civil – Superstructure | 165 | 150 | 13 | 2 | 20 | 19 | 5 | 495 | 480 | 380 | 365 | 5 | 5
Fit-Out & Finishes | 92 | 81 | 9 | 2 | 10 | 8 | 3 | 320 | 308 | 245 | 235 | 4 | 3
MEP Services | 118 | 102 | 14 | 2 | 14 | 13 | 4 | 390 | 375 | 285 | 274 | 5 | 4
TOTAL | Submittal Approval Rate |  |  |  | Audit Completion Rate |  |  | MIR Acceptance Rate |  | WIR Acceptance Rate |  | NCR Closure Rate
KPI RATES