## Company Infomation
Company Name | Company XYZ
Data Date | 2025-09-26
Submission Date | 2025-09-29

## Quality (hidden)
|  | Company Name | Company XYZ
|  | Data Date | 2025-09-26
|  | Template Description | This template aims to collect Safety metrics. The data should be cumulative up to data date
Sr. No | Company Name | Level 2 as highlighted in the WBS sheet | Level 3 as highlighted in the WBS sheet | All received technical submittals | Code A : Accepted with no comments | Code B : Accepted with comments | Code C : Rejected |  |  |  | Materials Inspection Request (MIR) Acceptance Rate |  | Work Inspection Request (WIR) Acceptance Rate
# | Level 1 | Level 2 | Level 3 | Total No. Of Received Technical Submittals | Total No. of Code A Technical Submittals | Total No. of Code B Technical Submittals | Total No. of Code C Technical Submittals | Total No. of Planned Quality Audits | Total No. of Conducted Quality Audits | No of Conducted Sr. Leadership Sites Visit | Total No. of Received MIRs | Total No. of Accepted MIRs | Total No. of Received WIRs | Total No. of Accepted WIRs | Total No. of Raised Quality NCRs | Total No. of Closed Quality NCRs | Construction - Actual Progress
2 | Diriyah | Diriyah I | DG1 Infrastructure | 5334 | 1460 | 4079 | 129 | 26 | 15 |  | 3210 | 8080 | 24978 | 62186 | 1047 | 833 | 40.53%
4 | Diriyah | Diriyah I | Diriyah Gardens |  |  |  |  | 0 | 0 | [7 empty] | 0.258%
2 | Diriyah | Diriyah I | Diriyah South | 383 | 26 | 59 | 22 | 5 | 5 |  | 150 | 98 | 2583 | 1847 | 6 | 16 | 18.33%
7 | Diriyah | Diriyah I | Diriyah Square | 12012 | 2301 | 4302 | 190 | 5 | 1 |  | 3377 | 3217 | 143369 | 55503 | 2276 | 2187 | 41.27%
2 | Diriyah | Diriyah I | Events | 684 | 217 | 96 | 9 | 0 | 4 |  | 151 | 285 | 1096 | 465 | 11 | 14 | 17.97%
6 | Diriyah | Diriyah I | King Salman Knowledge District | 4338 | 320 | 1804 | 35 | 8 | 1 |  | 2713 | 2332 | 22103 | 35633 | 276 | 192 | 23.23%
14 | Diriyah | Diriyah I | Qurain Cultural District | 7545 | 114 | 1207 | 231 | 57 | 14 |  | 2978 | 1731 | 26291 | 43880 | 567 | 306 | 51.96%
14 | Diriyah | Diriyah I | Site Wide |  |  |  |  | 2 | 4 | [7 empty] | 2.653%
9 | Diriyah | Diriyah II | Boulevard KSU |  |  |  |  | 0 | 1 | [7 empty] | 0.4566%
15 | Diriyah | Diriyah II | Boulevard North East |  |  |  |  | 1 | 1 | [7 empty] | 0.2483%
15 | Diriyah | Diriyah II | Boulevard North West |  |  |  |  | 1 | 5 | [7 empty] | 2.961%
20 | Diriyah | Diriyah II | Boulevard South East | 12 | 1 | 5 | 2 | 2 | 2 | [7 empty] | 1.497%
24 | Diriyah | Diriyah II | Boulevard South West | 41 | 2 | 17 | 7 | 2 | 2 | [7 empty] | 9.62%
9 | Diriyah | Diriyah II | BV - Boulevard Community |  |  |  |  | 0 | 0 | [7 empty] | 100%
27 | Diriyah | Diriyah II | Civic Quarter |  |  |  |  | 2 | 4 | [7 empty] | 0.4961%
20 | Diriyah | Diriyah II | Land Development | 1186 | 846 | 193 | 50 | 2 | 4 |  | 239 | 342 | 14512 | 16849 | 186 | 270 | 2.54%
22 | Diriyah | Diriyah II | Media & Innovation |  |  |  |  | 1 | 2 | [7 empty] | 2.13%
17 | Diriyah | Diriyah II | Northern East |  |  |  |  | 2 | 0 | [7 empty] | 2.812%
12 | Diriyah | Diriyah II | Northern West & Central |  |  |  |  | 2 | 1 | [7 empty] | 0.6807%
26 | Diriyah | Diriyah II | Primary Infrastructure | 1889 | 227 | 370 | 165 | 0 | 2 |  | 1095 | 823 | 4473 | 14081 | 323 | 402
11 | Diriyah | Diriyah II | Public Realm | 81 | 35 | 74 | 16 | 2 | 1 |  | 125 | 145 | 2479 | 1811 | 31 | 24
42 | Diriyah | Diriyah II | Site-Wide (DII) | 300 | 401 | 137 | 38 | 2 | 6 |  | 699 | 775 | 1371 | 1214 | 94 | 76
24 | Diriyah | Diriyah II | The Boulevard |  |  |  |  | 4 | 5 | [7 empty] | 2.956%
31 | Diriyah | Historic Diriyah | Wadi Hanifah General | 2972 | 3693 | 563 | 86 | 4 | 3 |  | 1305 | 1812 | 25891 | 15300 | 161 | 75 | 66.8%
26 | Diriyah | Wadi Safar | WS Assets & Infrastructure | 13346 | 1690 | 2723 | 248 | 2 | 1 |  | 3738 | 8535 | 83743 | 198398 | 1056 | 1066 | 74.01%
26 | Diriyah | Wadi Safar | WS Gateway Hotel |  |  |  |  | 4 | 1 | [7 empty] | 500%
49 | Diriyah | Wadi Safar | WS Hotels Packages 2&3 | 3619 | 408 | 1031 | 69 | 3 | 3 |  | 791 | 588 | 9219 | 19963 | 168 | 179 | 8.412%
17 | Diriyah | Wadi Safar | WS Hotels Stage 2 |  |  |  |  | 2 | 2 | [7 empty] | 0.2814%
20
18
40
62
37
68
23
33
30
31
53
48
28
75
44
57
81
54
32
80
94
37
31
95
27
38
57
49
80
91
92
58
83
39
54
81
34
83
68
135
136
94
73
91
127
131
139
110
124
131
103
60
66
117
98
57
59
124
59
57
168
174
182
87
62
178
69
96
67
202
68
111
155
82
198
116
202
206
65
213
76
163
225
206
202
191
139
125
112
231
244
141
123
129
164
96
235
229
141
182
146
258
85
69
185
227
213
94
88
207
125
200
139
105
162
90
136
168
147
115
188
289
216
257
155
234
285
246
215
82
251
290
223
158
321
252
110
324
153
220
145
140
166
226
232
195
264
193
225
348
341
219
118
139
309
234
116
95
265
161
230
178
323
379
316
385
103
156
138
176
380
119
291
400
385
178
324
169
126
262
292
126
290
214
235
160
290
395
318
427
190
232
195
202
324
125
205
284
325
457
243
252
198
172
313
137
359
232
222
355
300
277
238
236
135
460
222
328
293
267
161
268
306
455
388
332
476
403
299
144
190
264
223
429
268
152
189
439
357
311
509
538
297
360
448
399
198
336
435
237
271
163
504
365
143
409
556
419
496
513
525
523
490
247
334
368
184
489
319
469
311
490
586
215
521
613
307
413
313
496
365
323
363
513
309
441
224
257
375
500
642
355
508
545
625
252
479
455
319
372
446
592
167
322
314
275
389
571
466
499
647
623
624
390
657
346
260
464
518
270
416
493
407
380
328
203
226
429
666
254
647
605
381
575
689
592
433
335
190
294
621
410
367
717
663
239
444
313
657
326
666
734
764
516
646
709
630
755
651
357
682
656
462
450
481
731
695
443
481
650
280
493
442
480
546
530
757
286
346
359
442
598
363
426
273
632
626
547
765
687
636
274
423
642
611
811
234
803
604
703
222
576
522
616
647
769
778
836
445
719
445
500
668
719
252
621
568
638
394
703
356
863
773
254
631
834
806
907
257
315
889
669
370
704
419
284
500
622
570
451
701
570
582
625
522
669
497
322
721
259
793
294
600
471
908
313
911
285
276
498
450
266
883
403
492
377
733
934
367
827
474
727
968
514
630
424
874
875
1020
990
373
423
575
367
850
284
578
848
953
644
667
993
465
339
869
970
906
512
369
978
1057
574
967
881
391
847
1070
311
625
815
709
948
651
342
791
936
623
286
705
776
384
719
647
927
748
1002
435
724
460
1031
815
947
558
912
1110
834
1077
779
761
731
1131
1034
893
561
618
539
1139
377
575
751
540
1059
767
875
917
977
682
638
324
801
1167
628
483
796
515
661
1115
563
648
586
1202
911
1020
1203
585
872
314
833
500
392
553
1043
723
807
876
1084
555
1016
797
971
1039
813
770
1123
330
408
615
540
729
1023
565
629
996
912
695
802
885
862
672
755
1084
884
660
682
1042
787
601
637
582
561
449
1064
524
650
450
1088
877
1302
1110
1036
520
527
553
1088
828
616
1075
937
1335
1113
873
947
626
1341
440
1190
537
642
572
709
708
960
370
601
904
436
455
942
603
1350
556
371
929
1308
1328
1250
1046
726
455
867
1329
584
485
1172
1360
504
463
664
660
977
530
864
599
1209
820
1428
1138
1281
1266
968
1239
986
485
565
788
795
905
530
686
856
721
519
687
372
1204
1290
1331
965
436
844
961
950
1301
517
851
914
779
1244
610
1490
836
681
921
668
524
500
718
1008
971
1279
635
1340
1004
1206
940
1407
1489
1395
1281
549
467
1270
1047
899
440
575
857
431
941
472
749
1354
1454
1297
962
764
1286
1401
581
1357
1108
1232
1079
1054
612
727
1074
1242
1414
990
1221
1527
477
1333
583
1047
920
1066
642
1232
1459
408
1518
1353
1254
519
793
1470
1150
1430
1316
516
828
958
1537
681
1003
1311
1407
663
475
1662
907
741
1054
1546
447
1550
1255
610
881
653
1367
662
738
1443
1021
1466
984
1275
1414
1393
926
1362
1556
724
1214
819
1657
1470
710
573
997
1281
1129
1472
981
439
1014
1046
1638
1623
1439
741
1352
1541
1430
1145
1120
1570
1553
1213
1374
1101
829
932
1615
1228
923
1286
535
1097
1415
1227
1238
1783
760
1463
525
708
1479
1659
1131
657
1354
657
1531
1389
486
750
1295
1796
773
610
1419
1000
1152
1735
1274
1790
625
1133
1843
1554
1241
1111
1747
1463
1573
538
1730
606
947
1759
1869
1056
934
654
1358
671
1768
676
1380
812
1086
532
568
1138
589
1075
1210
1243
1359
775
978
1565
1322
1638
1876
848
829
839
643
1730
1266
1752
1883
977
1504
1679
779
961
1431
1793
1008
1429
1011
1854
509
1442
1080
1878
1611
815
644
1397
1201
1697
1107
1803
1364
1909
1009
1432
1116
905
1286
1488
718

## Devco input (raw - cumilative)
|  | Company Name | Company XYZ
|  | Data Date | 2025-09-26
|  | Template Description | This template aims to collect Quality metrics. The data should be cumulative up to data date
Sr. No | Company Name | Level 2 as highlighted in the WBS sheet | Level 3 as highlighted in the WBS sheet | This is needed in Safety to link leading and lagging indicators as agreed with PIF | Total cumulative sum of all hours worked by all workers on that project from its inception to the current date. | Total number of manhours worked without any lost-time incidents or injuries from last LTI till date. | A work-related incident or ill-health resulting in the death of one or more persons within the project. | An incident or ill-health resulting in a person being unable to carry work for one or more full workday or shift, not including the day or first shift of the incident or start of the ill-health. | The cumulative sum of manhours lost from LTI’s within a project from its inception to the current date. | Measures work-related injury or illness that requires medical treatment beyond first aid. This means that the injury or illness needs care from a professional healthcare provider, such as a physician or qualified paramedic, but does not result in time off work or restricted work duties. (Total incidents from project inception to the current date). | Captures the total near miss incidents or situation that could have resulted in an injury, illness, or damage, but did not, due to luck or intervention. (Total incidents from project inception to the current date). | Captures the total number of safety observations reported in a project from its inception till its current date. | captures the total number of documented project site safety walks conducted by leadership (CEO, CDO, project executives) from project inception till current date. | Captures the total number of formal HSE rewards, and recognitions provided to contractors & individuals as an appreciation for their high performance. (During this reporting month)
# | Level 1 | Level 2 | Level 3 | Project Names | Total No. of Manhours | Total safe manhours | No. of Fatality in the project | Lost Time Injury incidents | Lost Time Injury manhours | Total Recordable Incident | Total Near Miss incidents | Total Safety Observations | Total Leadership safety walks conducted | Total number of Recognitions & rewards
0 | NEOM | Oxagon | Oxagon - Sitewide |  | 22 | 27911248 | 0 | 0 | 0 | 0 | 0 | 100 | 38 | 5
4 | NEOM | Sindalah Island | Sindalah - Sitewide |  | 22 | 27911248 | 0 | 0 | 0 | 0 | 0 | 100 | 38 | 3492
3 | NEOM | Sindalah Island | Sindalah - Cluster 1 |  | 22 | 27911248 | 0 | 0 | 0 | 0 | 0 | 100 | 38 | 952
2 | NEOM | Sindalah Island | Sindalah - Cluster 2 |  | 22 | 27911248 | 0 | 0 | 0 | 0 | 0 | 100 | 38 | 63
4 | NEOM | Sindalah Island | Sindalah - Cluster 3 |  | 22 | 27911248 | 0 | 0 | 0 | 0 | 0 | 100 | 38 | 147
11 | NEOM | Sindalah Island | Sindalah - Cluster 4 |  | 22 | 27911248 | 0 | 0 | 0 | 0 | 0 | 100 | 38 | 82
10 | NEOM | Sindalah Island | Sindalah - Cluster 5 |  | 22 | 27911248 | 0 | 0 | 0 | 0 | 0 | 100 | 38 | 136
12 | NEOM | Sindalah Island | Sindalah - Cluster 6 |  | 22 | 27911248 | 0 | 0 | 0 | 0 | 0 | 100 | 38 | 80
14 | NEOM | Sindalah Island | Sindalah - Marine Assets |  | 22 | 27911248 | 0 | 0 | 0 | 0 | 0 | 100 | 38 | 57
7 | NEOM | Sindalah Island | Sindalah - Infrastructure |  | 22 | 27911248 | 0 | 0 | 0 | 0 | 0 | 100 | 38 | 341
14 | NEOM | Sindalah Island | Sindalah - Golf Course |  | 22 | 27911248 | 0 | 0 | 0 | 0 | 0 | 100 | 38 | 400
10 | NEOM | Sindalah Island | Sindalah - Mainland Assets |  | 22 | 27911248 | 0 | 0 | 0 | 0 | 0 | 100 | 38 | 118
17 | NEOM | Shushah |  |  | 22 | 27911248 | 0 | 0 | 0 | 0 | 0 | 100 | 38 | 33
8 | NEOM | Trojena |  |  | 22 | 27911248 | 0 | 0 | 0 | 0 | 0 | 100 | 38 | 5
27 | NEOM | NEOM Bay | NEOM Bay Airport Expansion - Terminal A & B Development |  | 22 | 27911248 | 0 | 0 | 0 | 0 | 0 | 100 | 38 | 13
10 | NEOM | THE LINE | LINE - Sitewide |  | 22 | 27911248 | 0 | 0 | 0 | 0 | 0 | 100 | 38 | 275
27 | NEOM | Gulf of Aqaba (Magna) | Magna - Sitewide |  | 22 | 27911248 | 0 | 0 | 0 | 0 | 0 | 100 | 38 | 3
30 | NEOM | Regional Infrastructure | Water/ Highways/ Special Projects & Energy |  | 22 | 27911248 | 0 | 0 | 0 | 0 | 0 | 100 | 38 | 0
14 | NEOM | Outer Regions | Outer Regions - Sitewide |  | 22 | 27911248 | 0 | 0 | 0 | 0 | 0 | 100 | 38 | 48
0
|  |  |  | Total | 418 | 530313712 | 0 | 0 | -530313294 | 0 | 0 | 1900 | 722 | 6250
KPI Ratings | [6 empty] | 0 | 0 |  | 0 | 0 | 909090.9091 | 345454.5455 | 2990430.622

## Final output sent to Platform
Project Name | A work-related incident or ill-health resulting in the death of one or more persons within the project. |  | An incident or ill-health resulting in a person being unable to carry work for one or more full workday or shift, not including the day or first shift of the incident or start of the ill-health. |  | Measures work-related injury or illness that requires medical treatment beyond first aid. This means that the injury or illness needs care from a professional healthcare provider, such as a physician or qualified paramedic, but does not result in time off work or restricted work duties. (Total incidents from project inception to the current date). |  | Captures the total near miss incidents or situation that could have resulted in an injury, illness, or damage, but did not, due to luck or intervention. (Total incidents from project inception to the current date). |  | Captures the total number of safety observations reported in a project from its inception till its current date. |  | Captures the total number of documented project site safety walks conducted by leadership (CEO, CDO, project executives) from project inception till current date. |  | Captures the total number of formal HSE rewards, and recognitions provided to contractors & individuals as an appreciation for their high performance. (During this reporting month)
| 1. 0 : Score 100% 2. > 0 and ≤ 0.01: Score 90% 3. 0.01 and ≤ 0.05: Score 80 4. 0.05 and ≤ 0.1: Score 070% 5. > 0.1: Score Zero |  | 0 : Score 100% > 0 and ≤ 0.04: Score 90% > 0.04 and ≤ 0.1: Score 80% > 0.1 and ≤ 0.2: Score 70% > 0.2: Score Zero |  | 0 : Score 100% > 0 and ≤ 0.045: Score 90% > 0.045 and ≤ 0.09: Score 80% > 0.09 and ≤ 0.15: Score 70% > 0.15: Score Zero |  | > 5.0: Score 100% 3.0 - 5.0: Score 90% 1.0 - 3.0: Score 80% < 1.0: Score 70% 0: Score Zero |  | > 100: Score 100% 80 - 100: Score 90% 60 - 80: Score 80% 40 - 60: Score 70% < 40: Score Zero |  | > 7.0: Score 100% 5.0 - 7.0: Score 95% 3.0 - 5.0: Score 90% 2.0 - 3.0: Score 85% < 2.0: Score 80% 0: Score Zero |  | > 0.4: Score 100% 0.3 - 0.4: Score 95% 0.2 - 0.3 : Score 90% 0.1 - 0.2: Score 85% < 0.1 : Score 80% 0: Score Zero
| No. of Fatality in the project |  | Lost Time Injury incidents |  | Total Recordable Incident |  | Total Near Miss incidents |  | Total Safety Observations |  | Total Leadership safety walks conducted |  | Total number of Recognitions & rewards
NEOM Combined | 0 | 100% | 0 | 100% | 0 | 100% | 0 | 0% | 909090.9091 | 100% | 345454.5455 | 100% | 2990430.622 | 100%
> 5.0: Score 100% 3.0 - 5.0: Score 90% 1.0 - 3.0: Score 80% < 1.0: Score 70% 0: Score Zero
[7 empty] | 0 | 0%
[7 empty] | #REF! | #REF!
[7 empty] | #REF! | #REF!
[7 empty] | #REF! | #REF!
3

## Dropdown (hidden)
Design Stage Status | Contract Type | Contract Award Status | Contract Work Status | Design Maturity at Award | Is Joint Venture | Is Main Package | Is Investor Funded | Source | Impact | Rating | Type | Status | Residential | Hospitality | Office | Retail | Entertainment & Sport | Education | Healthcare | Social Infrastructure | Transport/Logistic/Industrial | Other Accommodation | Parking | Mixed Use | Milestone Status | Delivery Status | Al Bahah Province | Al Jouf Province | Al Qassim Province | Al Madinah Province | Asir Province | Eastern Province | Hail Province | Jizan Province | Mecca Province | Najran Province | Northern Borders Province | Riyadh Province | Tabuk Province | Type | Category | Approval Status | Levels
Completed​ - On Time | Construction | Awarded | Not Started | Pre-Concept | Yes | Yes | Yes | Contractor | Cost | Very High | Risk | Open | Villas - (Unit value above SAR 5 mln) | Hyper Luxury (5 stars) | Grade A | Super Regional Mall | Cinema | Daycare Centre / Nursery | Medical Centre / Clinics (Primary Care) | Mosque | Terminal | Staff Accommodation | Parking | Mixed Use | New Actions (to be endorsed) | In Progress | Al-Bahah | Al Jouf | Buraydah | Madinah | Abha | Dhahran | Hail | Jizan | Jeddah | Najran | Turaif | Riyadh | Tabuk | Concern | General | Not Started | Level 1
Completed​ - Delayed | Design | In Tender | Suspended / On-hold | Concept | No | No | No | PMC | Reputation | High | Issue | Closed | Villas - (Unit value SAR 2.5 to 5 mln) | Luxury (5 stars) | Grade B | Regional Mall | Theme Park | Kindergarten | General Hospital (Secondary Care) | Red Crescent Center | Marinas | Labor Accommodation |  |  | Not Started Yet | Delivered | Al-Mandaq | Qurayyat | Al Rass | Yanbu | Khamis Mushayt | Dammam |  | Al-Shuqaiq | Taif | Sharoura | Arar | Al Kharj | Duba | Achievements | Schedule Performance | Pending Approval | Level 2
In Progress - On Track | Consultancy | To be Tendered | Withdrawn / Canceled | Developed/Schematic |  |  |  | Supplier | Time | Medium |  |  | Villas - (Unit value SAR 1.3 to 2.5 mln) | Upper upscale (5 stars) | Other Offices | Community | Family Entertainment Centers | K12 School | Specialty Hospital (Tertiary Care) | Police Station | Stations |  |  |  | In Progress - On Track | Not Started | Al-Aqiq |  | Unaizah | al-Ula | Asir | Ahsa |  |  | Mecca |  | Rafha | Sudair |  | Key Ask | Contract risk | Approved | Level 3
In Progress - Off Track | Design & Build |  | In - Progress | Detailed |  |  |  | Other | Other | Low |  |  | Villas - (Unit value SAR 0.68 to 1.3 mln) | Upscale (4 stars) |  | Neighborhood center | Museum/Art & Culture | University / University Branch | Other healthcare | Civil Defense | Warehouse |  |  |  | In Progress - Needs Attention | On Hold |  |  |  |  | Bisha | Ras Al Khair |  |  | Rabigh |  | Al-Uwayqilah | Majmaah |  |  | Scope change
In Progress - Needs Attention | Other |  | Completed | IFC |  |  |  | Client | Social |  |  |  | Villas - (Unit value SAR 0.45 to 0.68 mln) | Midscale (3 stars) |  | Strip/Convenience center | Theater | Training Centers |  | Central Library | Distribution Center |  |  |  | In Progress - Off Track | [5 empty] | Al Namas | Qatif |  |  | Shoaiba |  |  | Al Ghat |  |  | Lack of approval
Not Started Yet | [7 empty] | MOMRAH | Environment |  |  |  | Villas - (Unit value below SAR 0.45 mln) | Economy (1 and 2 stars) |  | Other Retail | Stadium /Arena | Other education |  | Post Office | Ambient Warehouse Storage |  |  |  | Completed - On Time | [6 empty] | Khobar |  |  | Qunfudhah |  |  | Dawadmi |  |  | Operational risk
[8 empty] | Civil Defense | Cost & Reputation |  |  |  | Apartments - (Unit value above SAR 5 mln) | Serviced Apartments (5 stars) |  |  | Golf Course |  |  | Other Social Infrastructure | Cold Storage |  |  |  | Completed - Delayed | [6 empty] | Jubail |  |  | Rabigh |  |  | Afif |  |  | Other
[8 empty] | SEC | Cost & Time |  |  |  | Apartments - (Unit value SAR 2.5 to 5 mln) | Serviced Apartments (4 stars) |  |  | Sports & Wellness |  |  |  | Manufacturing | [10 empty] | Hafr Al Batin | [5 empty] | Zulfi
[8 empty] | NWC | Repuation & Time |  |  |  | Apartments - (Unit value SAR 1.3 to 2.5 mln) | Serviced Apartments (3 stars) |  |  | Recreational Entertainment |  |  |  | Other Logistic/Industrial | [10 empty] | Khurais | [5 empty] | Majmaah
[8 empty] | STC | Cost & Reputation & Time |  |  |  | Apartments - (Unit value SAR 0.68 to 1.3 mln) | Other Hospitality |  |  | Other entertainment | [14 empty] | Empty Quarter | [5 empty] | Diriyah
[13 empty] | Apartments - (Unit value SAR 0.45 to 0.68 mln) | [18 empty] | Abqaiq | [5 empty] | Rimah
[13 empty] | Apartments - (Unit value below SAR 0.45 mln) | [18 empty] | Ras Tanura
[13 empty] | Townhouse - (Unit value above SAR 5 mln) | [18 empty] | Khafji
[13 empty] | Townhouse - (Unit value SAR 2.5 to 5 mln) | [18 empty] | Qurayyah
Townhouse - (Unit value SAR 1.3 to 2.5 mln)
Townhouse - (Unit value SAR 0.68 to 1.3 mln)
Townhouse - (Unit value SAR 0.45 to 0.68 mln)
Townhouse - (Unit value below SAR 0.45 mln)
Other Residential